## BurnDownSrint2
Tasks | Completion Time in Days on the 17/10/22 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | Days Work Per Week | Number of Weeks | Based on tutorial found here:
[6 empty] | 2.5 | 4 | https://www.extendoffice.com/documents/excel/2446-excel-burndown-chart-or-burn-up-chart.html
basic UI | 2
flow chart | 1
tavern map texturing |  |  |  | 1
character improvements | 5 | 2 | 1 | 1
stagger system blueprints |  | 4 | 1
character reset on ragdoll activate |  |  | 2
player dead UI |  |  |  | 0.5
old stagger system (outdated) | 2 | 1
Remaining work days | 10 | 7.5 | 5 | 2.5 | 0
Remaining days worth of work | 10 | 7 | 4 | 2.5 | 0