## BurnDownSrint2
Tasks | Completion Time in Days on the 21/11/23 | 2023-11-28 | 2023-12-05 | 2023-12-12 | 2023-12-15 | Days Work Per Week | Number of Weeks | Based on tutorial found here:
Research into Map Concepts | 1 | 0.5 | 0 | 0 | 0 | 2.5 | 4 | https://www.extendoffice.com/documents/excel/2446-excel-burndown-chart-or-burn-up-chart.html
1 Map Design | 2 | 1 | 0.5 | 0 | 0
Implementation of new traps | 2 | 1 | 0.5 | 0 | 0
Implementation of Timer | 1 | 0.5 | 0 | 0 | 0
Refinement of levels. | 2 | 1 | 0.5 | 0.5 | 0
Sounds | 2 | 1 | 0.5 | 0 | 0
Materials for spells | 0.5 | 0.5 | 0 | 0 | 0
Remaining work days | 10 | 7.5 | 5 | 2.5 | 0
Remaining days worth of work | 10.5 | 5.5 | 2 | 0.5 | 0