## BurnDownSrint2
Tasks | Completion Time in Days on the 16/10/23 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | Days Work Per Week | Number of Weeks | Based on tutorial found here:
Enemy Vision | 0 | 0 | 0 | 0 | 0 | 2.5 | 4 | https://www.extendoffice.com/documents/excel/2446-excel-burndown-chart-or-burn-up-chart.html
Enemy Vision(dot product research) | 0.5 | 0
Enemy Vision(dot product Test) | 0.2 | 0
Enemy Vision(onOverlap) | 0.3 | 0
Mantle/ climb up (removed) | 0 | 0 | 0 | 0 | 0
Mantle Research | 0.5 | 0
Mantle(transform .z change) | 0.2 | 0
Mantle(collision sphere) | 0.1 | 0
Mantle(collision sphere, disabled) | 0.2 | 0
Mantle(checking in air research) | 0.1 | 0
Mantle(checking if in air) | 0.3 | 0
Mantle(testing) | 0.1 | 0
Enemy Movement | 0 | 0 | 0 | 0 | 0
Research on local multiplayer | 0.3 | 0
Testing local multiplayer | 0.5 | 0
Cleaning up code | 0.1 | 0
Testing cleaned code | 0.3 | 0.2
Research interfaces | 0.6 | 0.4
Research oop inheritance | 0.1 | 0.1
Character controller | 0.1 | 0.1
Spells | 0 | 0 | 0 | 0 | 0
Randomized spell effects | 0.7 | 0.7
Cleaning up spell code | 0.2 | 0.2
Spell blueprinting (making it easier for designers) | 0.4 | 0.4
Spell Effects | 0.6 | 0.6
Bugfixing | 0.6 | 0.6
Spell pushing | 0.2 | 0.2
Spell pulling | 0.2 | 0.2
Spell spawning and despawning | 0.1 | 0.1
Spell Refactoring | 0 | 0 | 0 | 0 | 0
Creating interface system | 0.1 | 0 | 0
Bugfixing | 0.1 | 0 | 0
Research Game modes | 0.1 | 0.1
Fixing unintended split screen | 0.1 | 0.1
Fixing duplicated spawn | 0.1 | 0
Fix crashing | 0.1 | 0
Fix spell collisions not working as intended | 0.2 | 0.2
Level changes | 0.5 | 0.5
Ghost Spells (collision issue?) | 0.6 | 0.6
Spells crashing game (no bueno) | 0.2 | 0.2
Remaining work days | 10 | 7.5 | 5 | 2.5 | 0
Remaining days worth of work | 9.4 | 5.3 | 0 | 0 | 0