## BurnDownSrint3
Tasks | Completion Time in Days on the 14/11/22 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | Days Work Per Week | Number of Weeks | Based on tutorial found here:
King of the Hill zone creation | [5 empty] | 2.5 | 4 | https://www.extendoffice.com/documents/excel/2446-excel-burndown-chart-or-burn-up-chart.html
KOTH research | 2
KOTH implementation |  |  | 2 | 2
KOTH testing |  |  |  |  | 1
KOTH bugfixing |  |  |  |  | 2
Side effects research | 2 | 2
Side effects implementation |  |  | 2 | 2
Side effects testing
Side effects bugfixing | 3 |  |  |  | 1
General bugfixing | 2 | 4 |  |  | 2
Remaining work days | 10 | 7.5 | 5 | 2.5 | 0
Remaining days worth of work | 9 | 6 | 4 | 4 | 6