## BurnDownSrint2
Tasks | Completion Time in Days on the 17/10/22 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | Days Work Per Week | Number of Weeks | Based on tutorial found here:
Research into Map Concepts | 0.1 |  |  |  |  | 2.5 | 4 | https://www.extendoffice.com/documents/excel/2446-excel-burndown-chart-or-burn-up-chart.html
Creation of 2 map designs | 0.3
Implementation of Item Spawner |  | 0.1
Implementation of Teleporting Door |  | 0.1
Research into Map objective concepts |  |  | 0.1
Creation of 2 objective map designs |  |  | 0.2
Implementation Push and Pull system |  |  | 0.3
Remaining work days | 10 | 7.5 | 5 | 2.5 | 0
Remaining days worth of work | 0.4 | 0.2 | 0.6 | 0 | 0